## Overview
Field | Value
Project | RemoteSync - Employee Rotation & Presence Management
Repository | https://github.com/JdaidiHamza/RemoteSync
Prepared by | Maryam Alaoui Ismaili
Date | 2025-09-06
Scope Summary | Functional E2E testing of authentication, profile management, collaborator scheduling, request processing, project management. Focus on critical user journeys and role-based access (employee, RC/manager).
Environments | Local: Backend (Spring Boot), Frontend (Angular), Database (MySQL via Docker).

## Security
ID | Work Item Type | Title | Prerequisites | Steps | Expected Result | Comment | Test Status | Test Comment | Severity | Priority
RSYNC-SC-UC1.1 | Test Case | Direct URL access without login | Not logged in | 1) Try to access /dashboard directly | Redirected to login page | Ensure unauthorized users cannot bypass login | Passed | Attempted to navigate directly to the /dashboard URL without an active session. The application correctly enforced the security constraint and redirected to the login page as expected. | Major | P1
RSYNC-SC-UC1.2 | Test Case | SQL Injection attempt | Login page open | 1) Enter a SQL injection attempt in the username field to test input validation. | Input sanitized, error shown, no data leakage | Verify all user inputs are properly escaped/sanitized | Passed | Submitted a common SQL injection payload (' OR '1'='1) in the username field. The application correctly handled the input without executing the query, displaying a standard "Bad credentials" error. No data leakage or unexpected behavior was observed. | Critical | P1

## Frontend_TestCases
ID | Work Item Type | Title | Prerequisites | Steps | Expected Result | Comment | Test Status | Test Comment | Severity | Priority
RSYNC-FO-UC1.1-SN | Test Case | Authentication - Positive | Authentication page loaded; test account exists | 1) Enter username/email and password 2) Click Login | System authenticates user, creates secure session and redirects to dashboard according to role | Verify login redirection is role-based (RC, Collaborator). Ensure session token is stored securely. | Passed | Verified successful login for 'employee' and 'manager' roles, with correct dashboard redirection. (Automated in auth.spec.ts - 'Positive login - normal user' & 'Positive login - manager user') | Critical | P1
RSYNC-FO-UC1.1-SE1 | Test Case | Authentication - Negative (invalid creds) | Authentication page loaded | 1) Enter incorrect username/email or password 2) Click Login | System shows error 'Username or password incorrect' and does not create session | Ensures system rejects wrong credentials. | Passed | Entered correct username with wrong password. Login was blocked and the expected "Bad credentials" toast appeared. (Automated in auth.spec.ts - 'Login with wrong password shows error toast') | Major | P1
RSYNC-FO-UC1.1-SE2 | Test Case | Authentication - Disabled account | Auth page loaded; account flagged disabled | 1) Enter inactive user credentials 2) Click Login | System displays informative message that account is disabled and prevents login | Check for generic error messages to avoid leaking sensitive details. | Passed | Login with a known disabled account was correctly blocked and displayed an error toast containing 'disabled'. (Automated in auth.spec.ts - 'Login with disabled account shows disabled error') | Major | P1
RSYNC-FO-UC1.1-SA1 | Test Case | Forgot password - valid | Auth page loaded | 1) Click 'Forgot password' 2) Enter valid email 3) Submit | Password reset email is sent and confirmation shown in UI | Confirms reset email flow works with valid email. | Blocked | Could not complete test. The backend API returns a 500 Internal Server Error when submitting a valid email, preventing verification of the reset flow. (See bug report RSYNC-BUG-001) | Minor | P2
RSYNC-FO-UC1.1-SA2 | Test Case | Forgot password - invalid | Auth page loaded | 1) Click 'Forgot password' 2) Enter invalid or non-existent email 3) Submit | System shows 'email invalid or not found' message | Ensures proper error for both invalid/nonexistent email. | Passed | Entered a non-existent email address. Application correctly displayed an error toast: "User not found with email...". (Automated in auth.spec.ts - 'Forgot password: non existing user') | Minor | P2
RSYNC-FO-UC1.2-STATE | Test Case | Profile - Readonly fields state | User logged in; profile page opened | 1) Open profile page 2) Observe fields that are read-only | Non-editable fields are displayed and disabled/grayed out and cannot be edited | Validate that only non-sensitive fields are editable. Check accessibility for grayed-out inputs | Passed | Verified that 'Username' and 'Email' fields on the profile page were displayed correctly and were not editable. (Automated in profile.spec.ts - 'should display user information in readonly fields') | Minor | P2
RSYNC-FO-UC1.2-SN | Test Case | Profile - Edit and save (valid) | Profile page accessible; user logged in | 1) Modify editable fields with valid data 2) Save changes 3) Reload page | System persists changes and shows success message; updated values displayed after reload | Confirm data is updated in DB and reflected across sessions | Passed | Successfully updated the phone number. The change persisted after a page reload and a success toast was shown. (Automated in profile.spec.ts - 'should successfully update the phone number with valid data') | Major | P1
RSYNC-FO-UC1.2-SE1 | Test Case | Profile - Edit invalid input | Profile page accessible; user logged in | 1) Enter invalid data in fields 2) Attempt to save | Invalid field highlighted; explicit error message displayed; save action blocked | Ensures invalid profile input blocked with error. | Passed | Attempt to save an invalid phone number was correctly blocked and a specific validation error toast was displayed. (Automated in profile.spec.ts - 'should show an error when updating with an invalid phone number') | Major | P1
RSYNC-FO-UC1.3-SN | Test Case | Switch language | Logged in | 1) Open Settings → Change language (e.g. English → French) | UI instantly updates to new language | Verify i18n implementation, all labels translated correctly | Passed | Switched UI language to French. All visible labels and buttons correctly updated to the new language. (Automated in profile.spec.ts - 'should switch the UI language and persist the change') | Major | P1

## Team_Planning
ID | Work Item Type | Title | Prerequisites | Steps | Expected Result | Comment | Test Status | Test Comment | Severity | Priority
RSYNC-FO-UC3.1-SN | Test Case | Team planning - create rotation (happy path) | User logged in; role=RC; dates available; collaborators free | 1) RC creates new rotation: select project, collaborators, period, rotation template 2) Confirm | System validates capacity, creates assignments, notifies collaborators | Include capacity check and notifications | Passed | Manually tested. As an RC Manager, successfully created a new rotation with a valid project, dates, and collaborators. The new rotation appeared correctly on the team calendar. | Critical | P1
RSYNC-FO-UC3.1-SE1 | Test Case | Team planning - missing mandatory field | User logged in; role=RC | 1) Fill form leaving one required field empty 2) Confirm | Save blocked; field highlighted with clear error message | UI should prevent invalid submission | Passed | Manually tested. Attempted to submit the rotation form with the 'project' field left empty. The submission was correctly blocked, and a "This field is required" validation message was displayed. | Major | P1
RSYNC-FO-UC3.1-SE2 | Test Case | Team planning - invalid/illogical data | User logged in; role=RC | 1) Provide illogical dates or invalid data 2) Confirm | System blocks save and shows clear error message | Server-side validation required | Failed | CRITICAL FAILURE: Manually tested and discovered the system allows the creation of a rotation for a collaborator who already has a conflicting assignment. Expected: An error message blocking the creation. Actual: The conflicting rotation was created successfully. (See bug report RSY-BUG-003) | Major | P1
RSYNC-FO-UC3.1-SE3 | Test Case | Team planning - capacity exceeded | User logged in; role=RC; site capacity low | 1) Attempt to schedule beyond site capacity 2) Confirm | Operation blocked; alert about capacity exceeded; no calendar changes | Critical business logic | Not executed | Test was de-prioritized. Requires specific test data setup (a site with a defined capacity limit and a full schedule) that was not available during the assessment window. | Critical | P1
RSYNC-FO-UC3.1-MN1 | Test Case | Modify rotation using toggle | Logged in as RC, rotation exists | 1)Open calendar 2)Locate rotation 3)Use toggle (remote ↔ on-site) 4)Save | Rotation status updated immediately, UI refreshed, notifications sent | Modification | Passed | Manually tested. Successfully located an existing rotation on the calendar and used the toggle to change a collaborator's status from 'on-site' to 'remote'. The change was saved and reflected immediately. | Major | P1
RSYNC-FO-UC3.1-RG1 | Test Case | Unauthorized access | User logged in; role=Collaborator | 1) Attempt to access team planning functionality | System redirects to 'Access Denied' or shows unauthorized message | Check RBAC enforcement | Passed | Manually tested. Logged in with a 'Collaborator' role and attempted to navigate directly to the team planning URL. The application correctly redirected to an 'Access Denied' page. | Critical | P1

## Calendar_Requests
ID | Work Item Type | Title | Prerequisites | Steps | Expected Result | Comment | Test Status | Test Comment | Severity | Priority
RSYNC-FO-UC2.1-SN | Test Case | View personal shift calendar | User logged in; role=Collaborator | 1) Navigate to Calendar 2) View current month 3) Navigate to previous/next months | Calendar displays current month by default; work-on-site and remote days are color-coded per legend.(blue -> on-site /orange -> remote) | Ensure color legend visible | Passed with Exceptions | The primary user path via the Dashboard's 'Work Schedule' widget has failed due to a critical defect (RSYNC-BUG-002), resulting in a degraded user experience. The core functionality remains accessible via the secondary path (the main /calendar page), which passed both automated (collaborator.spec.ts) and manual verification. | Medium | P2
RSYNC-FO-UC2.2-SN | Test Case | Submit modification request - valid | User logged in; role=Collaborator | 1) Go to 'Reports' -> Create new request 2) Fill form with valid data 3) Submit | Success message shown; request saved and notification sent to RC | Verify notification mechanism | Passed | Successfully submitted a new modification request with all valid data. The application displayed a success notification toast as expected. (Automated in collaborator.spec.ts) | Major | P1
RSYNC-FO-UC2.2-SE1 | Test Case | Submit modification request - invalid | User logged in; role=Collaborator | 1) Create new request with invalid/missing fields 2) Submit | Submission blocked; invalid fields highlighted with specific messages | Check client-side & server-side validation | Passed | Attempted to submit a request with missing required fields. The submission was correctly blocked by client-side validation, and a field-level error message was displayed. (Automated in collaborator.spec.ts) | Major | P1

## Request_Processing
ID | Work Item Type | Title | Prerequisites | Steps | Expected Result | Comment | Test Status | Test Comment | Severity | Priority
RSYNC-FO-UC3.2-SN | Test Case | Process a modification request - approve | RC logged in; pending request exists | 1) RC selects pending request 2) Approve | Request status updated to approved; schedule updated; collaborator notified | Verify notifications and audit trail | Passed | Successfully approved a pending request. The application displayed a "Report updated successfully" toast, as verified by the automated test. (Automated in rc-reports.spec.ts) | Major | P1
RSYNC-FO-UC3.2-SA1 | Test Case | Process a modification request - reject | RC logged in; pending request exists | 1) RC selects pending request 2) Reject | Request status updated to 'Rejected'; no schedule change; collaborator notified | Verify notifications | Passed with Exceptions | The reject functionality works, but a significant usability defect was found: the application displays the same generic "Report updated successfully" message for both 'approve' and 'reject' actions. This is misleading and could cause user confusion. Recommendation: Implement distinct confirmation messages for each action. (Automated in rc-reports.spec.ts) | Major | P1

## Backoffice
ID | Work Item Type | Title | Prerequisites | Steps | Expected Result | Comment | Test Status | Test Comment | Severity | Priority
RSYNC-BO-UC1.1-SN | Test Case | Project management - create project (valid) | RC logged in | 1) RC fills new project form with valid data 2) Submit | Project is saved and success message displayed | Check uniqueness constraints | Passed | A new project was created with all valid data. The system displayed a success message, and the project appeared in the project list. | Major | P1
RSYNC-BO-UC1.1-SE1 | Test Case | Project management - duplicate project name | RC logged in; project with same name exists | 1) RC tries to create a project with an existing name 2) Submit | System blocks creation and shows explicit error about duplicate project name | DB unique constraint required | Failed | DEFECT FOUND: An attempt to create a project with a pre-existing name was not blocked. Expected: A unique constraint error. Actual: The system allowed the duplicate project to be created, leading to a data integrity issue. | Major | P1
RSYNC-BO-UC1.1-SE2 | Test Case | Create Project - Missing Required Fields | RC logged in | 1) Leave fields empty 2) Submit | System blocks creation and shows validation error messages per field | Validation constraints | Passed | Submission was correctly blocked when required fields were left empty. Field-level validation errors were displayed as expected. | Major | P1
RSYNC-BO-UC1.2-R | Test Case | Project management - view project list | RC logged in; at least 1 project exists | 1) RC navigates to Project Management 2) Observe list | All projects displayed with correct details; pagination, sorting and filtering work correctly | Data must match DB records | Passed | The project list view loaded and displayed all projects with correct data. Pagination and sorting controls were functional. | Medium | P2
RSYNC-BO-UC1.3-U | Test Case | Project management - update project (valid) | RC logged in; project exists | 1) RC opens project 2) Edit valid fields 3) Save | Project updated successfully, confirmation message displayed | Changes must persist in DB | Passed | Successfully edited an existing project with valid data. The changes were saved and correctly reflected in the project list. | Major | P1
RSYNC-BO-UC1.3-SE | Test Case | Project management - update project invalid | RC logged in; project exists | 1) RC opens project 2) Enter invalid/empty data 3) Save | System blocks update, highlights invalid fields, shows clear error messages | Validation constraints | Passed | An attempt to save a project with invalid data (e.g., an empty name) was correctly blocked by form validation. | Major | P1
RSYNC-BO-UC1.4-D | Test Case | Project management - delete project (valid) | RC logged in; project exists with no rotations | 1) RC selects project 2) Click delete 3) Confirm | Project deleted, removed from list, success message displayed | Verify database | Passed | Successfully deleted a project that had no associated rotations. The project was removed from the list after confirmation. | Major | P1
RSYNC-BO-UC1.4-SE | Test Case | Project management - delete project w/ links | RC logged in; project linked to rotations | 1) RC selects project 2) Click delete 3) Confirm | System blocks deletion and shows explicit warning that project is linked to active rotations | Business rule enforcement | Failed | CRITICAL DEFECT: The system allowed the deletion of a project that was actively linked to existing rotations. Expected: Deletion should be blocked. Actual: The project was deleted, risking orphaned rotation records and data corruption. | Critical | P2